## Risk Log
| Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens.
1 | Social and weather conditions (rainy season and COVID-19) may impact the fieldwork schedule in several cities in India where we plan to conduct face to face interviews through random street intercept. This could delay the completion of fieldwork and release of study findings from the target date of March 31, 2021. | Medium | High | High | Project Manager | None. | The fieldwork will need to be extended. The release of the study date may need to be revised. Key stakeholders to be notified
2 | No control over staff priorities | Medium | Medium | Medium | Project Manager | The Research Director will brief team managers on the importance of the project. Soft book resources as early as possible and then communicate final booking dates asap after the scheduling workshops. Identify back ups for each human resource on the project. | Escalate to the Research Director and bring in back up resource.
3 | It is likely that in spite of best efforts of the fieldwork team, sample counts for some models may not reach the sufficient sample count of 100 or more. Models with small (30-99 samples) and insufficient (less than 30 samples) will not be ranked in their respective segments. This may result in clients not subscribing to the study. | Medium | High | High | Project Manager | Rework the sample plan with the best knowledge at the time of launch | Open up regional and city level target sample quota. Collect samples from whereever possible
4 | Estimating and/or scheduling errors | Medium | High | High | Project Manager | Break this risk into two: 'cost estimating' and 'scheduling errors'. Use two methods of cost estimation, and carefully track costs and forecast cost at completion making adjustments as necessary. Build in 10% contingency on cost and scheduling. Track schedules daily and include schedule review as an agenda item in every project team meeting. Flag forecast errors and/or delays to the Project Board early. | Escalate to research director and project board. Raise change request for change to budget or schedule. Pull down contingency.
5 | Unplanned work that must be accommodated | Low | High | Medium | Team Manager | Attend project scheduling workshops. Check previous projects, for actual work and costs. Check all plans and quantity surveys. Document all assumptions made in planning and communicate to the project manager before project kick off. | Escalate to the Project Manager with plan of action, including impact on time, cost and quality.
6 | Lack of communication, causing lack of clarity and confusion. | Medium | Medium | Medium | Project Manager | Write a communication plan which includes frequency, goal, and audience of each communication. Identify stakeholders early and make sure they are considered I the communication plan. Use most appropriate channel of communication for audience e.g. don't send 3 paragraph email to Developers, have a call instead. | Correct misunderstandings immediately. Clarify areas that are not clear swiftly using assistance from Research Director if needed.
7 | Stakeholder action delays project. | Low | High | High | Project Manager | Identify stakeholders, analyse power and influence and create a stakeholder engagement plan. Project Board to authorise the plan. Revisit the plan at regular intervals to check all stakeholders are managed. Consider getting insurance. | Notify appropriate authorities and follow internal procedures e.g. for activist demonstrations.

## Severity
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High